## Invoices indexed by Contractor
Vendor | Date | Description | Amount | Notes
84 Lumber | 2014-10-23 | Lumber | 17053.58 | Blanco
84 Lumber | 2014-11-26 | Madera Ventanas Puertas | 13408.19 | Blanco
ABP Technology | 2014-10-21 | UTP cables, video cameras | 365.34 | Messer
ABP Technology | 2014-12-09 | Camera + AP | 235 | Messer
Amazon | 2013-12-18 | Kitchen faucets | 63.9
Amazon | 2013-12-18 | Bathroom faucet | 77.3051
Amazon | 2013-12-18 | Door Stops | 12.9353
Amazon | 2013-12-18 | Door handles | 153.95
Amazon | 2013-12-18 | Bathroom accessories | 37.8
Amazon | 2013-12-18 | Door handles | 73.62
Amazon | 2013-12-18 | Door handles keypad | 121.99
Amazon | 2013-12-18 | Closet Door pull | 21.8
Amazon | 2013-12-19 | Capital Lighting Vanity Mist Scavo Creek Stone | 79.9
Amazon | 2013-12-20 | Capital Lighting Vanity Mist Scavo Creek Stone | 63.95
Amazon | 2013-12-27 | 6x Capital Lighting Wall Lantern (Medium) | 227.34
Amazon | 2013-12-27 | 6x Capital Lighting Wall Lantern (Medium) | 105.32
Amazon | 2014-01-09 | 2x Capital Lighting Wall Lantern (Large) | 83.68
Amazon | 2014-08-09 | Kichler Lighting | 66.03
Amazon | 2014-08-09 | 1X Millennium Lighting (Flush Mounted) | 57.89
Amazon | 2014-08-09 | Door handles | 60.44
Amazon | 2014-08-09 | Door handles | 34.97
Amazon | 2014-08-14 | 1X MB Sink faucet | 231.49
Amazon | 2014-08-14 | 2x shower flange | 11.7
Amazon | 2014-08-14 | 2x shower faucets & valves | 536.22
Amazon | 2014-08-14 | 1X Tub faucet | 129.51
Amazon | 2014-08-19 | Powder Room Vanity Light | 31.54
Amazon | 2014-08-20 | 1X MB Sink faucet | 247.6
Amazon | 2014-08-26 | Door handles keypad | 175.79
Amazon | 2014-09-10 | Bathroom Drain | 15.9
Amazon | 2014-09-10 | Bathroom Faucet | 69.48
Amazon | 2014-11-08 | Wiring-networking (group of invoices) | 307.89 | Blanco
Amazon | 2014-12-06 | Monogram Brass | 27 | Messer
Amazon | 2014-12-06 | Yamaha natural sound 120 watts | 286.8 | Messer
Amazon | 2014-12-20 | Low Voltage | 34.53 | Messer
Ameri Surveyors | 2014-09-11 | Form Check Boundary | 535 | Messer
Associated Plumbing | 2014-10-09 | First Draw | 2000 | Blanco
Associated Plumbing | 2014-12-17 | Plumbing | 6950 | Blanco
ATG Stores | 2013-12-20 | Capital Lighting Vanity Mist Scavo Creek Stone | 79.9
ATG Stores | 2014-01-06 | 2X Millennium Lighting (Flush Mounted) | 94.6
BCL Quality Masonry Works, LLC | 2014-11-17 | Stone Work - Stucco work | 5000 | Blanco
BCL Quality Masonry Works, LLC | 2014-12-03 | Material for exterior Stucco Work | 5000 | Blanco
BCL Quality Masonry Works, LLC | 2014-12-11 | Stucco | 3250 | Blanco
BCL Quality Masonry Works, LLC | 2014-12-24 | Stone labor | 2885 | Messer
Blue Sky Propane | 2014-11-21 | Tank propane 250 gallons | 1790.04 | Blanco
Brooks Stone Ranch | 2014-12-10 | Stones | 3088.37 | Blanco
Cables 4 Sure | 2014-11-02 | Ethernet cables | 132.32 | Messer
Canyon Lake Water Service | 2014-08-14 | Temporary Water | 950
Canyon Lake Water Service | 2014-12-19 | Water | 44.44 | Blanco
Champion Termite & Pest Services Inc | 2014-10-17 | Bee in Tree | 270.63 | Messer
Comal County | 2013-12-30 | Certifcates | 16
Comal County Engineer's Office | 2014-08-06 | Permit | 25
DHGate | 2014-10-12 | Bathroom fixture | 147.07 | Messer
FedEx | 2014-09-28 | Copies | 31.21 | Messer
Geotechnical Solutions | 2013-12-04 | Soil Test | 265
Greg Setzer | 2013-11-01 | Architectural Design Review | 3874.5 | 1st Design
Greg Setzer | 2014-03-01 | Architectural Design Review | 843.75
Greg Setzer | 2014-06-01 | Architectural Design Review | 2150
High Sierra | 2014-08-13 | Portapotti | 243.56
High Sierra Toilet Co. Inc | 2014-11-15 | Const Unit (1/WK clean out) | 81.19 | Blanco
High Sierra Toilet Co. Inc | 2014-12-15 | Const Unit (1/WK clean out) | 75 | Blanco
Ikea | 2014-04-12 | Closet Transport | 85.52
Ikea | 2014-04-12 | Closet | 461.15
Impact Electric | 2014-12-24 | Rough In electrical wire | 6192 | Blanco
Lone Star | 2014-10-14 | Jet Prints | 17.54 | Messer
LoneStar | 2103-11-27 | Plans copies | 102.88 | 1st design
LoneStar | 2014-06-03 | Plans copies | 89.11
Lowes | 2013-10-23 | A+R Capistrano, Pfolio 3Lt, 3x DPR Pfolio | 452.3667
Lowes | 2013-11-25 | Portfolio 13IN 2LT/ 3LT NKHRN IRNSTN | 96.52
Lowes | 2013-11-25 | 9LT Linkhorn, 3LT Linkhorn, 5LT Linkhorn | 543.42
Lowes | 2014-01-12 | Dishwasher/Dryer | 846.44
Lowes | 2014-11-03 | PVC coupling | 67.27 | Messer
Lowes | 2014-11-17 | PVC adapter | 65.17 | Messer
Lowes | 2014-11-20 | PVC adapter | 31.34 | Messer
Lowes | 2014-11-26 | PVC adapter | 6.57 | Messer
Lowes | 2014-12-01 | BathTube Toilet Central water Thermostat | 6863.26 | Messer
Lowes | 2014-12-06 | Fireplace | 556.79 | Messer
Lowes | 2014-12-20 | Duct Tape | 84.45 | Messer
Metro | 2014-01-11 | Bathroom tile | 1400 | Partial payment. Total $2154.46
Morrison Supply Company | 2014-11-21 | Tub/ Sink/ Toilet | 2425.21 | Blanco
Mystic Shores POA | 2013-12-03 | Architectural review | 300
Mystic Shores POA | 2013-12-03 | Application fee | 1500
Paul Swoyer Septics,LLC | 2014-11-13 | Aerobic Septic Systems | 9260 | Blanco
Pedernales | 2014-08-22 | Electricity | 2323.68
Pedernales | 2014-12-19 | Electricity | 26.5 | Blanco
Platinum Tile Partners | 2014-08-06 | Title | 4424.86
Principal Custom Homes | 2014-08-12 | 10 Year Warranty for home | 1937
Privado (Craigs List) | 2014-01-08 | Mirrors | 90
Privado (Craigs List) | 2014-08-27 | Vanity/Faucte/Lamp | 300
R&J Construction Inc. | 2014-10-28 | FRAM | 5182 | Blanco
R&J Construction Inc. | 2014-11-11 | FRAM | 5200 | Blanco
R&J Construction Inc. | 2014-11-14 | FRAM | 4300 | Blanco
R&J Construction Inc. | 2014-12-16 | FRAM | 1927 | Blanco
Ranger Concrete | 2013-11-12 | Site work | 4100
Ranger Concrete | 2014-08-28 | Excavation & Construction Road | 11478
Ranger Concrete | 2014-09-26 | Load Bull Rock | 825 | Messer
Ranger Concrete | 2014-10-17 | Foundation | 43994.7 | Blanco
RD Drywall | 2014-12-12 | Drywall | 3500 | Blanco
Ring | 2014-12-06 | Ring Video Dorbell | 199 | Messer
Rosin Group | 2013-07-24 | Survey | 300
RVOS | 2014-08-09 | Insurance | 284.75
RVOS | 2014-11-21 | Insurance | 304.75 | Blanco
San Marcos Doors | 2014-08-29 | Main Door | 2684.76
San Marcos Doors | 2014-12-10 | Main Door | 536.96 | Messer
San Marcos Group LLC | 2014-10-14 | Main Door | 2147.8 | Blanco
Septic Sustems Express | 2013-12-30 | Septic Design & Inspections | 780
Termimesh | 2014-10-13 | Termite | 510.31 | Blanco
Texas Disposal Systems | 2014-08-13 | Waste | 1144.28
Texas Dispossal System | 2014-11-03 | Waste | 657.54 | Blanco
Texas Dispossal System | 2014-11-07 | Waste | 457.96 | Blanco
Texas Dispossal System | 2014-12-19 | Waste | 1212 | Blanco
The Central Roof Company | 2014-10-29 | Roof | 4913 | Blanco
The Central Roof Company | 2014-12-02 | Roof | 5896 | Blanco
The Central Roof Company | 2014-12-22 | Roof | 9017.22 | Messer
Ubuildit | july 17 2013 | Contract Signing | 2700
Ubuildit | 2014-05-26 | Re-Bidding | 625
Ubuildit | 2014-06-03 | Re-Bidding | 625
Ubuildit | 2014-08-12 | Completion of Planning Phase @ closing at the bank | 7829
Ubuildit | 2014-10-13 | Completion of Slab | 4893 | Blanco
Ubuildit | 2014-11-04 | Framing Rafters | 3914 | Blanco
Westbrook Engineering | 2013-12-13 | Foundation Design | 599.64 | 1st Design: US$225 Onsite inspection
Westbrook Engineering | 2013-12-13 | Foundation Design | 553.66
Westbrook Engineering | 2014-07-02 | Foundation | 27
Westbrook Engineering | 2014-09-11 | Inspection | 300
Westside | 2014-08-17 | Wall plates + switch + outlets | 91.21
Westside | 2014-08-17 | Bath Fan+ light | 146.79
Westside Wholesale | 2013-12-08 | switches, outlets | 583.2
Westside Wholesale | 2014-10-18 | Switches, wall plates, networking items | 386.01 | Messer
249708.5471

## Invoices indexed by date
INVOICES
| Date | Vendor | Description | Amount | Notes
0 | 2013-07-17 | Ubuildit | Contract Signing | 2700
1 | 2013-07-24 | Rosin Group | Survey | 300
2 | 2013-10-23 | Lowes | A+R Capistrano, Pfolio 3Lt, 3x DPR Pfolio | 452.3667
3 | 2013-11-01 | Greg Setzer | Architectural Design Review | 3874.5 | 1st Design
4 | 2013-11-12 | Ranger Concrete | Site work | 4100
5 | 2013-11-25 | Lowes | Portfolio 13IN 2LT/ 3LT NKHRN IRNSTN | 96.52
6 | 2013-11-25 | Lowes | 9LT Linkhorn, 3LT Linkhorn, 5LT Linkhorn | 543.42
7 | 2103-11-27 | LoneStar | Plans copies | 102.88 | 1st design
8 | 2013-12-03 | Mystic Shores POA | Architectural review | 300
9 | 2013-12-03 | Mystic Shores POA | Application fee | 1500
10 | 2013-12-04 | Geotechnical Solutions | Soil Test | 265
11 | 2013-12-08 | Westside Wholesale | switches, outlets | 583.2
12 | 2013-12-13 | Westbrook Engineering | Foundation Design | 599.64 | 1st Design: US$225 Onsite inspection
13 | 2013-12-13 | Westbrook Engineering | Foundation Design | 553.66
14 | 2013-12-18 | Amazon | Kitchen faucets | 63.9
15 | 2013-12-18 | Amazon | Bathroom faucet | 77.3051
16 | 2013-12-18 | Amazon | Door Stops | 12.9353
17 | 2013-12-18 | Amazon | Door handles | 153.95
18 | 2013-12-18 | Amazon | Bathroom accessories | 37.8
19 | 2013-12-18 | Amazon | Door handles | 73.62
20 | 2013-12-18 | Amazon | Door handles keypad | 121.99
21 | 2013-12-18 | Amazon | Closet Door pull | 21.8
22 | 2013-12-19 | Amazon | Capital Lighting Vanity Mist Scavo Creek Stone | 79.9
23 | 2013-12-20 | Amazon | Capital Lighting Vanity Mist Scavo Creek Stone | 63.95
24 | 2013-12-20 | ATG Stores | Capital Lighting Vanity Mist Scavo Creek Stone | 79.9
25 | 2013-12-27 | Amazon | 6x Capital Lighting Wall Lantern (Medium) | 227.34
26 | 2013-12-27 | Amazon | 6x Capital Lighting Wall Lantern (Medium) | 105.32
27 | 2013-12-30 | Comal County | Certifcates | 16
28 | 2013-12-30 | Septic Sustems Express | Septic Design & Inspections | 780
29 | 2014-01-06 | ATG Stores | 2X Millennium Lighting (Flush Mounted) | 94.6
30 | 2014-01-08 | Privado (Craigs List) | Mirrors | 90
31 | 2014-01-09 | Amazon | 2x Capital Lighting Wall Lantern (Large) | 83.68
32 | 2014-01-11 | Metro | Bathroom tile | 1400 | Partial payment. Total $2154.46
33 | 2014-01-12 | Lowes | Dishwasher/Dryer | 846.44
34 | 2014-03-01 | Greg Setzer | Architectural Design Review | 843.75
35 | 2014-04-12 | Ikea | Closet Transport | 85.52
36 | 2014-04-12 | Ikea | Closet | 461.15
37 | 2014-05-26 | Ubuildit | Re-Bidding | 625
38 | 2014-06-03 | Ubuildit | Re-Bidding | 625
39 | 2014-06-01 | Greg Setzer | Architectural Design Review | 2150
40 | 2014-06-03 | LoneStar | Plans copies | 89.11
41 | 2014-07-02 | Westbrook Engineering | Foundation | 27
42 | 2014-08-06 | Platinum Tile Partners | Title | 4424.86
43 | 2014-08-06 | Comal County Engineer's Office | Permit | 25
44 | 2014-08-09 | Amazon | Kichler Lighting | 66.03
45 | 2014-08-09 | Amazon | 1X Millennium Lighting (Flush Mounted) | 57.89
46 | 2014-08-09 | Amazon | Door handles | 60.44
47 | 2014-08-09 | Amazon | Door handles | 34.97
48 | 2014-08-09 | RVOS | Insurance | 284.75
49 | 2014-08-12 | Principal Custom Homes | 10 Year Warranty for home | 1937
50 | 2014-08-12 | Ubuildit | Completion of Planning Phase @ closing at the bank | 7829
51 | 2014-08-13 | Texas Disposal Systems | Waste | 1144.28
52 | 2014-08-13 | High Sierra | Portapotti | 243.56
53 | 2014-08-14 | Canyon Lake Water Service | Temporary Water | 950
54 | 2014-08-14 | Amazon | 1X MB Sink faucet | 231.49
55 | 2014-08-14 | Amazon | 2x shower flange | 11.7
56 | 2014-08-14 | Amazon | 2x shower faucets & valves | 536.22
57 | 2014-08-14 | Amazon | 1X Tub faucet | 129.51
58 | 2014-08-17 | Westside | Wall plates + switch + outlets | 91.21
59 | 2014-08-17 | Westside | Bath Fan+ light | 146.79
60 | 2014-08-19 | Amazon | Powder Room Vanity Light | 31.54
61 | 2014-08-20 | Amazon | 1X MB Sink faucet | 247.6
62 | 2014-08-22 | Pedernales | Electricity | 2323.68
63 | 2014-08-26 | Amazon | Door handles keypad | 175.79
64 | 2014-08-27 | Privado (Craigs List) | Vanity/Faucte/Lamp | 300
65 | 2014-08-29 | San Marcos Doors | Main Door | 2684.76 | Blanco
66 | 2014-09-10 | Amazon | Bathroom Drain | 15.9
67 | 2014-09-10 | Amazon | Bathroom Faucet | 69.48
68 | 2014-09-11 | Westbrook Engineering | Inspection | 300
69 | 2014-08-28 | Ranger Concrete | Excavation & Construction Road | 11478
70 | 2014-09-11 | Ameri Surveyors | Form Check Boundary | 535 | Messer
71 | 2014-09-28 | FedEx | Copies | 31.21 | Messer
72 | 2014-09-26 | Ranger Concrete | Load Bull Rock | 825 | Messer
73 | 2014-10-09 | Associated Plumbing | First Draw | 2000 | Blanco
75 | 2014-10-12 | DHGate | Bathroom fixture | 147.07 | Messer
76 | 2014-10-13 | Ubuildit | Completion of Slab | 4893 | Blanco
77 | 2014-10-13 | Termimesh | Termite | 510.31 | Blanco
78 | 2014-10-14 | Lone Star | Jet Prints | 17.54 | Messer
79 | 2014-10-14 | San Marcos Group LLC | Main Door | 2147.8 | Blanco
80 | 2014-10-18 | Westside Wholesale | Switches, wall plates, networking items | 386.01 | Messer
81 | 2014-10-17 | Champion Termite & Pest Services Inc | Bee in Tree | 270.63 | Messer
82 | 2014-10-17 | Ranger Concrete | Foundation | 43994.7 | Blanco
83 | 2014-10-21 | ABP Technology | UTP cables, video cameras | 365.34 | Messer
84 | 2014-10-23 | 84 Lumber | Lumber | 17053.58 | Blanco
85 | 2014-10-28 | R&J Construction Inc. | FRAM | 5182 | Blanco
86 | 2014-10-29 | The Central Roof Company | Roof | 4913 | Blanco
87 | 2014-11-02 | Cables 4 Sure | Ethernet cables | 132.32 | Messer
88 | 2014-11-03 | Texas Dispossal System | Waste | 657.54 | Blanco
89 | 2014-11-03 | Lowes | PVC coupling | 67.27 | Messer
90 | 2014-11-04 | Ubuildit | Framing Rafters | 3914 | Blanco
91 | 2014-11-07 | Texas Dispossal System | Waste | 457.96 | Blanco
92 | 2014-11-08 | Amazon | Wiring-networking (group of invoices) | 307.89 | Blanco
93 | 2014-11-11 | R&J Construction Inc. | FRAM | 5200 | Blanco
94 | 2014-11-13 | Paul Swoyer Septics,LLC | Aerobic Septic Systems | 9260 | Blanco
95 | 2014-11-14 | R&J Construction Inc. | FRAM | 4300 | Blanco
96 | 2014-11-15 | High Sierra Toilet Co. Inc | Const Unit (1/WK clean out) | 81.19 | Blanco
97 | 2014-11-17 | BCL Quality Masonry Works, LLC | Stone Work - Stucco work | 5000 | Blanco
98 | 2014-11-17 | Lowes | PVC adapter | 65.17 | Messer
99 | 2014-11-20 | Lowes | PVC adapter | 31.34 | Messer
100 | 2014-11-21 | Morrison Supply Company | Tub/ Sink/ Toilet | 2425.21 | Blanco
101 | 2014-11-21 | Blue Sky Propane | Tank propane 250 gallons | 1790.04 | Blanco
102 | 2014-11-21 | RVOS | Insurance | 304.75 | Blanco
103 | 2014-11-26 | Lowes | PVC adapter | 6.57 | Messer
104 | 2014-11-26 | 84 Lumber | Madera Ventanas Puertas | 13408.19 | Blanco
105 | 2014-12-01 | Lowes | BathTube Toilet Central water Thermostat | 6863.26 | Messer
106 | 2014-12-02 | The Central Roof Company | Roof | 5896 | Blanco
107 | 2014-12-03 | BCL Quality Masonry Works, LLC | Material for exterior Stucco Work | 5000 | Blanco
108 | 2014-12-06 | Ring | Ring Video Dorbell | 199 | Messer
109 | 2014-12-06 | Amazon | Monogram Brass | 27 | Messer
110 | 2014-12-06 | Amazon | Yamaha natural sound 120 watts | 286.8 | Messer
111 | 2014-12-06 | Lowes | Fireplace | 556.79 | Blanco
112 | 2014-12-09 | ABP Technology | Camera + AP | 235 | Messer
113 | 2014-12-10 | Brooks Stone Ranch | Stones | 3088.37 | Blanco
114 | 2014-12-10 | San Marcos Doors | Main Door | 536.96 | Blanco
115 | 2014-12-11 | BCL Quality Masonry Works, LLC | Stucco | 3250 | Blanco
116 | 2014-12-12 | RD Drywall | Drywall | 3500 | Blanco
117 | 2014-12-15 | High Sierra Toilet Co. Inc | Const Unit (1/WK clean out) | 75 | Blanco
118 | 2014-12-16 | R&J Construction Inc. | FRAM | 1927 | Blanco
119 | 2014-12-17 | Associated Plumbing | Plumbing | 6950 | Blanco
120 | 2014-12-19 | Texas Dispossal System | Waste | 1212 | Blanco
121 | 2014-12-19 | Pedernales | Electricity | 26.5 | Blanco
122 | 2014-12-19 | Canyon Lake Water Service | Water | 44.44 | Blanco
123 | 2014-12-20 | Amazon | Low Voltage | 34.53 | Messer
124 | 2014-12-20 | Lowes | Duct Tape | 84.45 | Messer
125 | 2014-12-22 | The Central Roof Company | Roof | 9017.22 | Blanco
126 | 2014-12-24 | BCL Quality Masonry Works, LLC | Stone labor | 2885 | Blanco
127 | 2014-12-24 | Impact Electric | Rough In electrical wire | 6192 | Blanco
128 | 2014-12-26 | Ikea | Kitchen | 5443.7236 | Blanco
129 | 2014-12-26 | Ikea | Appliance (Vent Hood) | 464.3925 | Messer
130 | 2014-12-26 | Ikea | Hardware | 242.1769 | Messer
131 | 2014-12-26 | Ikea | Bathroom | 1171.6547 | Blanco
132 | 2014-12-26 | Ikea | Closets | 1187.7796 | Messer
133 | 2014-12-30 | Cool Component | HVAC | 4920 | Blanco
134 | 2015-01-06 | 84 Lumber | Lumber | 736.92 | Blanco
135 | 2015-01-06 | Lowes | Washer | 718.83 | Messer
136 | 2015-01-06 | South Texas Insulation | Insulation | 8120 | Blanco
137 | 2015-01-06 | RD Drywall | 2nd Draw | 2500 | Blanco
138 | 2015-01-06 | Impact Electric | Light outlet | 150 | Blanco
275364.0244

## Invoices indexed by Category
Classified line | Date | Vendor | Description | Amount | Total | Messer | Blanco | Notes
0 | 2013-11-01 | Greg Setzer | Architectural Design Review | 3874.5 |  | 3874.5 | 0 | 1st Design
0 | 2014-03-01 | Greg Setzer | Architectural Design Review | 843.75 |  | 843.75 | 0
0 | 2103-11-27 | LoneStar | Plans copies | 102.88 |  | 102.88 | 0 | 1st design
0 | 2014-08-27 | Privado (Craigs List) | Vanity/Faucte/Lamp | 300 |  | 300 | 0
0 | 2014-01-08 | Privado (Craigs List) | Mirrors | 90 |  | 90 | 0
0 | 2013-07-24 | Rosin Group | Survey | 300 |  | 300 | 0
[5 empty] | 5511.13 | 5511.13 | 0
1 | 2013-12-03 | Mystic Shores POA | Architectural review | 300 |  | 300 | 0
1 | 2014-08-06 | Comal County Engineer's Office | Permit | 25 |  | 25 | 0
1 | 2013-12-03 | Mystic Shores POA | Application fee | 1500 |  | 1500 | 0
[5 empty] | 1825 | 1825 | 0
2 | 2013-12-13 | Westbrook Engineering | Foundation Design | 553.66 |  | 553.66 | 0
2 | 2014-07-02 | Westbrook Engineering | Copy | 27 |  | 27 | 0
[5 empty] | 580.66 | 580.66 | 0
3 | 2014-09-11 | Ameri Surveyors | Form Check Boundary | 535 |  | 535 | 0
3 | 2013-12-13 | Westbrook Engineering | On site inspection + charge | 265.15 |  | 265.15 | 0 | 1st Design not included: U$319.49 + $15 copy
[5 empty] | 800.15 | 800.15 | 0
4 | 2014-06-01 | Greg Setzer | Architectural Design Review | 2150 |  | 2150 | 0
4 | 2014-06-03 | LoneStar | Plans copies | 89.11 |  | 89.11 | 0
4 | 2014-10-14 | Lone Star | Jet Prints | 17.54 |  | 17.54 | 0
4 | 2014-09-28 | FedEx | Copies | 31.21 |  | 31.21 | 0
[5 empty] | 2287.86 | 2287.86 | 0
5 | 2013-12-04 | Geotechnical Solutions | Soil Test | 265 |  | 265 | 0
5 | 2014-09-11 | Westbrook Engineering | Inspection | 300 |  | 300 | 0
[5 empty] | 565 | 565 | 0
6 | 2014-08-09 | RVOS | Insurance | 284.75 |  | 284.75 | 0
6 | 2014-11-21 | RVOS | Insurance | 304.75 |  | 0 | 304.75
[5 empty] | 589.5 | 284.75 | 304.75
7 | 2014-08-12 | Principal Custom Homes | 10 Year Warranty for home | 1937 |  | 1937 | 0
[5 empty] | 1937 | 1937 | 0
8 | july 17 2013 | Ubuildit | Contract Signing | 2700 |  | 2700 | 0
8 | 2014-05-26 | Ubuildit | Re-Bidding | 625 |  | 625 | 0
8 | 2014-06-03 | Ubuildit | Re-Bidding | 625 |  | 625 | 0
[5 empty] | 3950 | 3950 | 0
9 | 2014-08-12 | Ubuildit | Completion of Planning Phase @ closing at the bank | 7829 |  | 7829 | 0
9 | 2014-10-13 | Ubuildit | Completion of Slab | 4893 |  | 0 | 4893
9 | 2014-11-04 | Ubuildit | Framing Rafters | 3914 |  | 0 | 3914
[5 empty] | 16636 | 7829 | 8807
19 | 2014-08-22 | Pedernales | Electricity | 2323.68 |  | 0 | 2323.68
19 | 2014-12-19 | Pedernales | Electricity | 26.5 |  | 0 | 26.5
[5 empty] | 2350.18 | 0 | 2350.18
21 | 2014-08-14 | Canyon Lake Water Service | Temporary Water | 950 |  | 0 | 950
21 | 2014-12-19 | Canyon Lake Water Service | Water | 44.44 |  | 0 | 44.44
[5 empty] | 994.44 | 0 | 994.44
23 | 2014-08-13 | High Sierra | Portapotti | 243.56 |  | 243.56 | 0
23 | 2014-11-15 | High Sierra Toilet Co. Inc | Const Unit (1/WK clean out) | 81.19 |  | 0 | 81.19
23 | 2014-12-15 | High Sierra Toilet Co. Inc | Const Unit (1/WK clean out) | 75 |  | 0 | 75
[5 empty] | 399.75 | 243.56 | 156.19
26 | 2013-12-30 | Comal County | Certifcates | 16 |  | 16 | 0
26 | 2013-12-30 | Septic Sustems Express | Septic Design & Inspections | 780 |  | 780 | 0
26 | 2014-11-13 | Paul Swoyer Septics,LLC | Aerobic Septic Systems | 9260 |  | 0 | 9260
[5 empty] | 10056 | 796 | 9260
33 | 2014-11-21 | Blue Sky Propane | Tank propane 250 gallons | 1790.04 |  | 0 | 1790.04
[5 empty] | 1790.04 | 0 | 1790.04
36 | 2014-08-13 | Texas Disposal Systems | Waste | 1144.28 |  | 1144.28 | 0
36 | 2014-11-03 | Texas Disposal Systems | Waste | 657.54 |  | 0 | 657.54
36 | 2014-11-07 | Texas Dispossal System | Waste | 457.96 |  | 0 | 457.96
36 | 2014-12-19 | Texas Dispossal System | Waste | 1212 |  | 0 | 1212
[5 empty] | 3471.78 | 1144.28 | 2327.5
37 | 2013-11-12 | Ranger Concrete | Site work | 4100 |  | 4100 | 0
[5 empty] | 4100 | 4100 | 0
38 | 2014-08-28 | Ranger Concrete | Excavation | 9528 |  | 0 | 9528 | In the same invoice than below
[5 empty] | 9528 | 0 | 9528
40 | 2014-08-28 | Ranger Concrete | Construction Road | 1950 |  | 0 | 1950 | In the same invoice than previous
[5 empty] | 1950 | 0 | 1950
47 | 2014-10-13 | Termimesh | Termite | 510.31 |  | 0 | 510.31
47 | 2014-10-17 | Champion Termite & Pest Services Inc | Bee in Tree | 270.63 |  | 0 | 270.63
[5 empty] | 780.94 | 0 | 780.94
48 | 2014-09-26 | Ranger Concrete | Load Bull Rock | 825 |  | 825
| 2014-10-17 | Ranger Concrete | Foundation | 43994.7 |  | 0 | 43994.7
[5 empty] | 44819.7 | 825 | 43994.7
50 | 2014-11-26 | 84 Lumber | Wood for framing | 7016.19 |  | 0 | 7016.19
50 | 2014-10-23 | 84 Lumber | Lumber | 17053.58 |  | 0 | 17053.58
50 | 2015-01-06 | 84 Lumber | Lumber | 736.92 |  | 0 | 736.92
[5 empty] | 24806.69 | 0 | 24806.69
| 2014-11-11 | R&J Construction Inc. | FRAM | 5200 |  | 0 | 5200
51 | 2014-11-14 | R&J Construction Inc. | FRAM | 4300 |  | 0 | 4300
51 | 2014-10-28 | R&J Construction Inc. | FRAM | 5182 |  | 0 | 5182
| 2014-12-16 | R&J Construction Inc. | FRAM | 1927 |  | 0 | 1927
[5 empty] | 16609 | 0 | 16609
56 | 2014-10-29 | The Central Roof Company | Roof | 4913 |  | 0 | 4913
56 | 2014-12-02 | The Central Roof Company | Roof | 5896 |  | 0 | 5896
56 | 2014-12-22 | The Central Roof Company | Roof | 9017.22 |  | 0 | 9017.22
[5 empty] | 19826.22 | 0 | 19826.22
58 | 2014-12-10 | Brooks Stone Ranch | Stones | 3088.37 |  | 0 | 3088.37
58 | 2014-12-24 | BCL Quality Masonry Works, LLC | Stone labor | 2885 |  | 0 | 2885
[5 empty] | 5973.37 | 0 | 5973.37
60 | 2014-12-06 | Lowes | Fireplace | 556.79 |  | 0 | 556.79
[5 empty] | 556.79 | 0 | 556.79
62 | 2014-10-09 | Associated Plumbing | First Draw | 2000 |  | 0 | 2000
62 | 2014-12-20 | Lowes | Duct Tape, galvanized ducts | 84.45 |  | 84.45 | 0
| 2014-12-17 | Associated Plumbing | Plumbing | 6950 |  | 0 | 6950
[5 empty] | 9034.45 | 84.45 | 8950
63 | 2014-12-01 | Lowes | Thermostat | 205.75 |  | 205.75 | 0
63 | 2014-12-30 | Cool Component | HVAC | 4920 |  | 0 | 4920
[5 empty] | 5125.75 | 205.75 | 4920
64 | 2014-08-17 | Westside Wholesale | Wall plates + switch + outlets | 91.21 |  | 91.21 | 0
64 | 2013-12-08 | Westside Wholesale | switches, outlets | 583.2 |  | 583.2 | 0
64 | 2014-10-18 | Westside Wholesale | Switches, wall plates, networking items | 386.01 |  | 386.01 | 0
64 | 2014-12-06 | Ring | Ring Video Dorbell | 199 |  | 199 | 0
64 | 2014-12-24 | Impact Electric | Rough In electrical wire | 6192 |  | 0 | 6192
64 | 2015-01-06 | Impact Electric | Light outlet | 150 |  | 0 | 150
[5 empty] | 7601.42 | 1259.42 | 6342
65 | 2014-10-21 | ABP Technology | UTP cables, video cameras | 365.34 |  | 365.34 | 0
65 | 2014-11-20 | Lowes | PVC adapter | 31.34 |  | 31.34 | 0
65 | 2014-11-26 | Lowes | PVC adapter | 6.57 |  | 6.57 | 0
65 | 2014-12-06 | Amazon | Yamaha natural sound 120 watts | 286.8 |  | 286.8 | 0
65 | 2014-11-02 | Cables 4 Sure | Ethernet cables | 132.32 |  | 132.32 | 0
65 | 2014-11-03 | Lowes | PVC coupling | 67.27 |  | 67.27 | 0
65 | 2014-11-08 | Amazon | Wiring-networking (group of invoices) | 307.89 |  | 0 | 307.89
65 | 2014-11-17 | Lowes | PVC adapter | 65.17 |  | 65.17 | 0
65 | 2014-12-01 | Lowes | Iris | 685.78 |  | 685.78 | 0
65 | 2014-12-09 | ABP Technology | Camera + AP | 235 |  | 235 | 0
65 | 2014-12-20 | Amazon | Low Voltage | 34.53 |  | 34.53 | 0
[5 empty] | 2218.01 | 1910.12 | 307.89
66 | 2014-11-26 | 84 Lumber | Windows | 4283.4525 |  | 0 | 4283.4525
[5 empty] | 4283.4525 | 0 | 4283.4525
68 | 2014-11-26 | 84 Lumber | Ext doors | 2108.5475 |  | 0 | 2108.5475
[5 empty] | 2108.5475 | 0 | 2108.5475
69 | 2014-08-29 | San Marcos Doors | Main Door | 2684.76 |  | 2684.76 | 0
69 | 2014-10-14 | San Marcos Group LLC | Main Door | 2147.8 |  |  | 2147.8
69 | 2014-12-10 | San Marcos Doors | Main Door | 536.96 |  | 0 | 536.96
[5 empty] | 5369.52 | 2684.76 | 2684.76
77 | 2015-01-06 | South Texas Insulation | Insulation | 8120 |  | 0 | 8120
[5 empty] | 8120 | 0 | 8120
78 | 2014-12-12 | RD Drywall | Drywall | 3500 |  | 0 | 3500
78 | 2015-01-06 | RD Drywall | 2nd Draw | 2500 |  | 0 | 2500
[5 empty] | 6000 | 0 | 6000
79 | 2014-10-22 | BCL Quality Masonry Works, LLC | Stone Work - Stucco work | 5000 |  | 0 | 5000
79 | 2014-12-03 | BCL Quality Masonry Works, LLC | Material for exterior Stucco Work | 5000 |  | 0 | 5000
79 | 2014-12-11 | BCL Quality Masonry Works, LLC | Stucco | 3250 |  | 0 | 3250
[5 empty] | 13250 | 0 | 13250
84 | 2014-12-01 | Lowes | Firetable | 388.73 |  | 388.73 | 0
[5 empty] | 388.73 | 388.73 | 0
87 | 2014-01-12 | Lowes | Dishwasher/Dryer | 846.44 |  | 846.44 | 0
87 | 2014-12-01 | Lowes | Refrigerator/Range/Microwave oven/trash disp | 2946.18 |  | 2946.18 | 0
87 | 2014-12-26 | Ikea | Appliance (Vent Hood) | 464.3925 |  | 464.3925 | 0
87 | 2015-01-06 | Lowes | Washer | 718.83 |  | 718.83 | 0
[5 empty] | 4975.8425 | 4975.8425 | 0
89 | 2013-12-19 | Amazon | Capital Lighting Vanity Mist Scavo Creek Stone | 79.9 |  | 79.9 | 0
89 | 2013-12-20 | Amazon | Capital Lighting Vanity Mist Scavo Creek Stone | 63.95 |  | 63.95 | 0
89 | 2013-12-27 | Amazon | 6x Capital Lighting Wall Lantern (Medium) | 227.34 |  | 227.34 | 0
89 | 2013-12-27 | Amazon | 6x Capital Lighting Wall Lantern (Medium) | 105.32 |  | 105.32 | 0
89 | 2014-01-09 | Amazon | 2x Capital Lighting Wall Lantern (Large) | 83.68 |  | 83.68 | 0
89 | 2014-08-09 | Amazon | Kichler Lighting | 66.03 |  | 66.03 | 0
89 | 2014-08-09 | Amazon | 1X Millennium Lighting (Flush Mounted) | 57.89 |  | 57.89 | 0
89 | 2014-08-19 | Amazon | Powder Room Vanity Light | 31.54 |  | 31.54 | 0
89 | 2014-08-20 | Amazon | 1X MB Sink faucet | 247.6 |  | 247.6 | 0
89 | 2014-09-10 | Amazon | Bathroom Drain for 2nd bath | 15.9 |  | 15.9 | 0
89 | 2014-09-10 | Amazon | Bathroom Faucet for 2nd Bath | 69.48 |  | 69.48 | 0
89 | 2013-12-20 | ATG Stores | Capital Lighting Vanity Mist Scavo Creek Stone | 79.9 |  | 79.9 | 0
89 | 2014-01-06 | ATG Stores | 2X Millennium Lighting (Flush Mounted) | 94.6 |  | 94.6 | 0
89 | 2013-10-23 | Lowes | A+R Capistrano, Pfolio 3Lt, 3x DPR Pfolio | 452.3667 |  | 452.3667 | 0
89 | 2013-11-25 | Lowes | Portfolio 13IN 2LT/ 3LT NKHRN IRNSTN | 96.52 |  | 96.52 | 0
89 | 2013-11-25 | Lowes | 9LT Linkhorn, 3LT Linkhorn, 5LT Linkhorn | 543.42 |  | 543.42 | 0
89 | 2014-10-12 | DHGate | Bathroom fixture | 147.07 |  | 147.07 | 0
89 | 2014-08-17 | Westside Wholesale | Bath Fan+ light | 146.79 |  | 146.79 | 0
89 | 2014-12-01 | Lowes | LED fluorescents lights | 321.99 |  | 321.99 | 0
[5 empty] | 2931.2867 | 2931.2867 | 0
90 | 2014-12-26 | Ikea | Kitchen | 5443.72 |  | 0 | 5443.72
90 | 2014-12-26 | Ikea | Bathroom | 1171.6547 |  | 0 | 1171.6547
[5 empty] | 6615.3747 | 0 | 6615.3747
96 | 2014-01-11 | Metro | Bathroom tile bath surrounds | 623.09 |  | 0 | 623.09
[5 empty] | 623.09 | 0 | 623.09
101 | 2013-12-18 | Amazon | Door Stops | 12.9353 |  | 12.9353 | 0
101 | 2013-12-18 | Amazon | Door handles | 153.95 |  | 153.95 | 0
101 | 2013-12-18 | Amazon | Door handles | 73.62 |  | 73.62 | 0
101 | 2013-12-18 | Amazon | Door handles keypad | 121.99 |  | 121.99 | 0
101 | 2013-12-18 | Amazon | Closet Door pull | 21.8 |  | 21.8 | 0
101 | 2014-08-09 | Amazon | Door handles | 60.44 |  | 60.44 | 0
101 | 2014-08-09 | Amazon | Door handles | 34.97 |  | 34.97 | 0
101 | 2014-08-26 | Amazon | Door handles keypad | 175.79 |  | 175.79 | 0
101 | 2014-04-12 | Ikea | Closet Transport | 85.52 |  | 85.52 | 0
101 | 2014-04-12 | Ikea | Closet | 461.15 |  | 461.15 | 0
101 | 2014-12-26 | Ikea | Closets | 1187.78 |  | 1187.78 | 0
[5 empty] | 2389.9453 | 2389.9453 | 0
106 | 2014-01-11 | Metro | Bathroom tile floor | 776.91 |  | 0 | 776.91
[5 empty] | 776.91 | 0 | 776.91
108 | 2013-12-18 | Amazon | Kitchen faucets | 63.9 |  | 63.9 | 0
108 | 2013-12-18 | Amazon | Bathroom faucet | 77.3051 |  | 77.3051 | 0
108 | 2013-12-18 | Amazon | Bathroom accessories | 37.8 |  | 37.8 | 0
108 | 2014-08-14 | Amazon | 1X MB Sink faucet | 231.49 |  | 231.49 | 0
108 | 2014-08-14 | Amazon | 2x shower flange | 11.7 |  | 11.7 | 0
108 | 2014-08-14 | Amazon | 2x shower faucets & valves | 536.22 |  | 536.22 | 0
108 | 2014-08-14 | Amazon | 1X Tub faucet | 129.51 |  | 129.51 | 0
108 | 2014-11-21 | Morrison Supply Company | Tub/ Sink/ Toilet | 2425.21 |  | 0 | 2425.21
108 | 2014-12-06 | Amazon | Monogram Brass | 27 |  | 27 | 0
108 | 2014-12-01 | Lowes | BathTube Toilet Central water softner | 2314.84 |  | 2314.84 | 0
[5 empty] | 5854.9751 | 3429.7651 | 2425.21
111 | 2014-12-26 | Ikea | Hardware | 242.18 |  | 242.18 | 0
[5 empty] | 242.18 | 242.18 | 0
121 | 2014-08-06 | Platinum Tile Partners | Title | 4424.86 |  | 4424.86
[5 empty] | 4424.86 | 4424.86 | 0
0
|  |  | In Budget |  | 269518.4143 | 52095.3696 | 217423.0447
|  |  | Total Budgeted |  | 360544 | 26544 | 334000
|  |  | Execution |  | 74.75% | 196.3% | 65.1%
|  |  | With additionals out of budget |  | 275029.5443 | 57606.4996 | 217423.0447
|  | Blanco | 217423.0447 | 211231.0447
|  | Pending | 104631.3347
322054.3794

## UBI Cost Review
|  | Project Cost Total ---------> | 360544
UBuildIt - Client Cost Review
|  | NAME: Tim & Maritza Messer | [7 empty] | Date: | 2015-10-05
| LINE | Cost Category/Detail | Notes | Budget | Actual | Change Orders | Over/(Under) Budget | Paid by Blanco | Remaining payments | Total Cost | Explanations / Options / Details
Pre-Construction Costs (Permits/Fees)
103 | 1 | Construction Permits |  | 0 | 1825 |  | 1841 | 0 | 0 | 1825 |  | 1
101 | 2 | Engineering Fees (Structural) | Foundation inspection + design allowance |  | 580.66 |  | 580.66 | 0 | 0 | 580.66 |  | 1
101 | 2 | Engineering Fees (Mechanical) |  | 0 |  |  | 0 |  |  | 800.15 |  | 1
101 | 3 | Engineering Fees (Other) | Form or Slab surveys | 400 | 800.15 |  | 400.15 | 0 | 0 | 2287.86 | Verify requirement with lender | 1
101 | 4 | Architect Fees |  |  | 2287.86 |  | 2287.86 | 0 | 0 | 2287.86 |  | 1
101 | 5 | Soils Study Fees |  | 0 | 565 |  | 565 | 0 | 0 |  |  | 1
101 | 6 | Project Insurance | Client Builder's Risk & General Liability Policy | 955 | 589.5 |  | -365.5 | 304.75 | 0 | 589.5 |  | 1
106 | 7 | Structural Warranty | 10 years by Principal Custom Homes, LLC | 1937 | 1937 |  | 0 |  | 0 | 1937 |  | 1
206 | 8 | UBuildIt Phase I Consulting Fee | UBuildIt (Phase I Fee) |  | 3950 |  | 3950 | 0 | 0 | 3950 |  | 1
| S.1 | Total Pre-Construction Costs (Permits/Fees) |  | 3292 | 12535.17 | 0 | 9243.17 | 304.75 | 0 | 12535.17
Site Development Costs
206 | 9 | UBuildIt Phase II Consulting Fee | UBuildIt (Phase II Fee) | 19572 | 16636 |  | -2936 | 8807 | 2936 | 16636 |  | 1
104 | 10 | Utility Connection Fees |  |  |  |  | 0 |  |  | 0 |  | 1
201 | 18 | Power (temporary) | Consumption during construction |  |  |  | 0 |  |  | 0 |  | 1
404 | 19 | Permanent power connection | Allowance | 3000 | 2350.18 |  | -649.82 | 2350.18 | 649.82 | 2350.18 |  | 1
201 | 20 | Water (temporary) | During construction | 0 |  |  | 0 |  |  | 0 |  | 1
201 | 21 | Water Meter | Allowance | 2500 | 994.44 |  | -1505.56 | 994.44 | 1505.56 | 994.44 |  | 1
307 | 22 | Water (Domestic Well) | Allowance |  |  |  | 0 |  |  | 0 |  | 1
204 | 23 | Temporary sanitation | Porta Potti allowance | 570 | 399.75 |  | -170.25 | 156.19 | 170.25 | 399.75 |  | 1
305 | 24 | Sanitation | Sewer connection allowance |  |  |  | 0 |  |  | 0 |  | 1
306 | 25 | Sanitation | Gravity System allowance |  |  |  | 0 |  |  | 0 |  | 1
306 | 26 | Sanitation | Aerobic System allowance | 9000 | 10056 |  | 1056 | 9260 | 0 | 10056 | Includes engineering & permits | 1
807 | 33 | On-site fuel tank (permanent) | Propane fuel tank allowance | 2500 | 1790.04 |  | -709.96 | 1790.04 | 0 | 1790.04 |  | 1
405 | 34 | Ditch Digging (Underground Utilities) | Water/Gas/Power/ Communication allowance | 400 |  |  | -400 |  | 500 | 0 |  | 1
304 | 35 | Rockeries or retaining walls (if applicable) |  | 0 |  |  | 0 |  |  | 0 |  | 1
309 | 36 | Dumpster | Allowance | 2800 | 3471.78 |  | 671.78 | 2327.5 | 500 | 3471.78 | Varify approved providers with city | 1
301 | 36 | Demolition | Allowance |  |  |  | 0 |  |  | 0 |  | 1
| S.2 | Total Site Development Costs |  | 40342 | 35698.19 | 0 | -4643.81 | 25685.35 | 6261.63 | 35698.19
Site Preparation
302 | 37 | Clearing | Tree removal allowance |  | 4100 |  | 4100 | 0 | 0 | 4100 |  | 1
303 | 38 | Excavation & Backfill | Allowance | 15000 | 9528 |  | -5472 | 9528 | 0 | 9528 |  | 1
819 | 39 | Fine Grading of Fill |  | 0 |  |  | 0 |  |  | 0 |  | 1
303 | 40 | Driveway Base | Two inch rock base | 0 | 1950 |  | 1950 | 1950 | 0 | 1950 |  | 1
303 | 41 | Finish Gravel |  | 0 |  |  | 0 |  |  | 0 |  | 1
821 | 42 | Driveway Topping | Asphalt | 0 |  |  | 0 |  |  | 0 |  | 1
821 | 43 | Driveway Topping | Concrete Allowance | 16005 |  |  | -16005 |  | 16005 | 0 | $3.75 sq.ft. | 1
309 | 44 | Erosion control | Filter fence, plastic, straw bales, etc. |  |  |  | 0 |  |  | 0 |  | 1
| S.3 | Total Site Preparation Costs |  | 31005 | 15578 | 0 | -15427 | 11478 | 16005 | 15578
Foundation
304 | 45 | Waterproofing (if applicable) |  | 0 |  |  | 0 |  |  | 0 |  | 1
305 | 46 | French Drain | Perforated pipe & rock | 0 |  |  | 0 |  |  | 0 |  | 1
| S.4 | Total Foundation Costs |  | 0 | 0 | 0 | 0 |  |  | 0
Slab Work
401 | 47 | Slab - Pest Control | Preventative Pest Control allowance | 1100 | 780.94 |  | -319.06 | 780.94 | 0 | 780.94 |  | 1
401 | 48 | Slab--TURNKEY BID | Labor & materials | 44000 | 44819.7 |  | 819.7 | 43994.7 | 0 | 44819.7 |  | 1
407 | 49 | Slab - Misc. Rental Equipment | Compactor, hammer drill, etc. |  |  |  | 0 |  |  | 0 |  | 1
| S.5 | Total Slab Work Costs |  | 45100 | 45600.64 | 0 | 500.64 | 44775.64 | 0 | 45600.64
Main Structure
502 | 50 | Framing Lumber | Lumber bid plus 10% contingency allowance | 26320 | 24806.69 |  | -1513.31 | 24806.69 | 0 | 24806.69 |  | 1
507 | 51 | Framing Labor | Contractor's bid | 16410 | 16609 |  | 199 | 16609 | 0 | 16609 |  | 1
501 | 52 | Structural Masonry | Labor & Material |  |  |  | 0 |  |  | 0 |  | 1
506 | 53 | Trusses | Other (specifiy) |  |  |  | 0 |  |  | 0 |  | 1
503 | 54 | Structural Steel |  | 0 |  |  | 0 |  |  | 0 |  | 1
507 | 55 | Misc. Labor | Other (Dentil Details) |  |  |  | 0 |  |  | 0 |  | 1
| S.6 | Total Main Structure Costs |  | 42730 | 41415.69 | 0 | -1314.31 | 41415.69 | 0 | 41415.69
General Trades
603 | 56 | Roofing | Materials//Labor | 17156 | 19826.22 |  | 2670.22 | 19826.22 | 0 | 19826.22 | Galvalume | 1
603 | 57 | Roofing | Other (specifiy) |  |  |  | 0 |  |  | 0 |  | 1
611 | 58 | Masonry - Exterior Veneer | Stone Material | 5038 | 5973.37 |  | 935.37 | 5973.37 | 6750 | 5973.37 |  | 1
611 | 59 | Masonry - Exterior Veneer | Labor |  |  |  | 0 |  |  | 0 |  | 1
513 | 60 | Masonry - Fireplace | Firebox materials & installation allowance | 1500 | 556.79 |  | -943.21 | 556.79 | 1121 | 556.79 |  | 1
513 | 61 | Masonry - Fireplace | Stone veneer |  |  |  | 0 |  |  | 0 |  | 1
509 | 62 | Plumbing | Labor & materials excluding fixtures | 10800 | 9034.45 |  | -1765.55 | 8950 | 1765.55 | 9034.45 |  | 1
510 | 63 | HVAC System | Labor & materials | 8200 | 5125.75 |  | -3074.25 | 4920 | 3074.25 | 5125.75 | 5 tons 16seer Comfort maker | 1
511 | 64 | Electric | Labor & materials excluding fixtures | 9526 | 7601.42 |  | -1924.58 | 6342 | 1924.58 | 7601.42 | Includes recess fixtures & vent fans | 1
511 | 65 | Rough-in low voltage allowance | Wiring for phone, TV, computer & security syst. | 1500 | 2218.01 |  | 718.01 | 307.89 | 0 | 2218.01 |  | 1
604 | 66 | Windows | Vinyl with low-E insulated glass | 3778 | 4283.4525 |  | 505.4525 | 4283.4525 | 0 | 4283.4525 |  | 1
606 | 67 | Skylights |  | 0 |  |  | 0 |  |  | 0 |  | 1
605 | 68 | Exterior Doors | Metal door units | 2076 | 2108.5475 |  | 32.5475 | 2108.5475 | 0 | 5369.52 |  | 1
605 | 69 | Exterior Doors | Front door allowance | 5500 | 5369.52 |  | -130.48 | 2684.76 | 0 | 0 |  | 1
613 | 70 | Garage Doors | Raised panel metal doors | 1300 |  |  | -1300 |  | 1450 | 0 | insulated | 1
613 | 71 | Garage Door Opener(s) | Belt drive units installed | 750 |  |  | -750 |  | 750 | 0 |  | 1
810 | 72 | Vacuum System | Rough-in allowance |  |  |  | 0 |  |  | 0 |  | 1
810 | 73 | Vacuum System | Equipment allowance |  |  |  | 0 |  |  | 0 |  | 1
825 | 74 | General Clean-up Labor |  | 0 |  |  | 0 |  |  | 0 |  | 1
512 | 75 | Fire sprinklers |  | 0 |  |  | 0 |  |  | 0 |  | 1
815 | 76 | Venting (Appliances) | Cooktop & dryer piping allowance |  |  |  | 0 |  |  | 0 | In a/c bid | 1
701 | 77 | Insulation | Spray foam walls and attic | 6835 | 8120 |  | 1285 | 8120 | 0 | 8120 |  | 1
702 | 78 | Drywall | Labor & materials including texture | 10470 | 6000 |  | -4470 | 6000 | 4750 | 6000 | Hand trowel walls,mont ceilings | 1
610 | 79 | Stucco | Labor & materials including painting | 13205 | 13250 |  | 45 | 13250 | 0 | 13250 |  | 1
705 | 80 | Painting/Staining Interior & Exterior | Labor & materials including cabnt finish | 13560 |  |  | -13560 |  | 11000 | 0 |  | 1
602 | 81 | Gutters and Downspouts | Allowance | 1000 |  |  | -1000 |  | 0 | 0 |  | 1
807 | 82 | Decks & Rails | Labor & materials allowance | 10000 |  |  | -10000 |  | 10000 | 0 |  | 1
612 | 83 | Iron & Metal Work | Allowance | 2500 |  |  | -2500 |  | 0 | 0 | Breezeway gates | 1
822 | 84 | Landscaping | Allowance | 3000 | 388.73 |  | -2611.27 | 0 | 2611.27 | 388.73 |  | 1
823 | 85 | Irrigation | Allowance | 0 |  |  | 0 |  |  | 0 |  | 1
824 | 86 | Fencing including gates | Allowance | 0 |  |  | 0 |  |  | 0 |  | 1
| S.7 | Total General Trades Costs |  | 127694 | 89856.26 | 0 | -37837.74 | 83323.03 | 45196.65 | 89856.26
Interior Finishing
806 | 87 | Appliances |  | 6500 | 4975.8425 |  | -1524.1575 | 0 | 0 | 4975.8425 |  | 1 | Allowance
806 | 88 | Appliances | Appliance installation allowance | 600 |  |  | -600 |  | 600 | 0 |  | 1
814 | 89 | Lighting Fixtures | Allowance | 3100 | 2931.2867 |  | -168.7133 | 0 | 0 | 2931.2867 |  | 1
704 | 90 | Cabinets | Materials excluding staining & installation | 11884 | 6615.3747 |  | -5268.6253 | 6615.3747 | 1950 | 6615.3747 | Includes $2000 for Family room | 1
801 | 91 | Countertops | Granite tops allowance | 5950 |  |  | -5950 |  | 5950 | 0 |  | 1
801 | 92 | Countertops | Cultured marble tops, sinks & splashes |  |  |  | 0 |  |  | 0 |  | 1
801 | 93 | Countertops | Kitchen tile backsplash allowance | 477 |  |  | -477 |  | 560 | 0 | $2.50 tile meterial Allowance | 1
801 | 94 | Decorative tile allowance |  | 300 |  |  | -300 |  | 300 | 0 |  | 1
802 | 95 | Surrounds | Tile at tubs allowance for labor & materials | 1446 |  |  | -1446 |  | 1100 | 0 | $2.50 tile meterial Allowance | 1
802 | 96 | Surrounds | Tile at showers allowance for labor & materials | 2401 | 623.09 |  | -1777.91 | 623.09 | 1400 | 623.09 | $2.50 tile meterial Allowance | 1
706 | 97 | Millwork & Doors | Interior door units | 1413 |  |  | -1413 | 0 | 3500 | 0 |  | 1
705 | 98 | Millwork & Doors | Millwork & Trim | 1870 |  |  | -1870 |  | 1870 | 0 | Includes 10% contigency allowance | 1
703 | 99 | Stairs & Rails | Material | 0 |  |  | 0 |  |  | 0 |  | 1
703 | 100 | Stairs & Rails | Labor to install | 0 |  |  | 0 |  |  | 0 |  | 1
708 | 101 | Finish Carpentry | Labor including doors, trim, cabinets & hdwr | 5431 | 2389.9453 |  | -3041.0547 | 0 | 3041.0547 | 2389.9453 |  | 1
825 | 102 | General Clean-up Labor |  |  |  |  | 0 |  |  | 0 |  | 1
825 | 103 | Floors | Stained concrete allowance |  |  |  | 0 |  |  | 0 |  | 1
804 | 104 | Floors | Hardwood Allowance | 12135 |  |  | -12135 |  | 9883 | 0 | $8.00 sq. ft. allowance | 1
804 | 105 | Floors | Tile labor allowance | 593 |  |  | -593 |  | 750 | 0 |  | 1
804 | 106 | Floors | Tile material allowance | 620 | 776.91 |  | 156.91 | 776.91 | 0 | 776.91 | $2.50 tile meterial Allowance | 1
805 | 107 | Floors | Carpet Allowance | 2961 |  |  | -2961 | 2425.21 | 3554 | 0 | $25.00 per sq. yard allowance | 1
812 | 108 | Plumbing Fixtures | Allowance including water heaters & softener | 8920 | 5854.9751 |  | -3065.0249 |  | 0 | 5854.9751 |  | 1
818 | 109 | Interior Glass - Shower Doors | Shower door & glass panels | 930 |  |  | -930 |  | 930 | 0 |  | 1
818 | 110 | Interior Glass - Mirrors | Vanity mirrors allowance | 250 |  |  | -250 |  | 0 | 0 |  | 1
707 | 111 | Finish Hardware | Allowance | 1250 | 242.18 |  | -1007.82 | 0 | 650 | 242.18 | Includes rail closets | 1
803 | 112 | Wall coverings | Wallpapers | 0 |  |  | 0 |  |  | 0 |  | 1
807 | 113 | Masonry, Interior | Veneers | 0 |  |  | 0 |  |  | 0 |  | 1
809 | 114 | Intercom |  | 0 |  |  | 0 |  |  | 0 |  | 1
816 | 115 | Solar Backup |  | 0 |  |  | 0 |  |  | 0 |  | 1
820 | 116 | Pool | Allowance |  |  |  | 0 |  |  | 0 |  | 1
705 | 117 | Fireplace Mantles | Allowance | 500 |  |  | -500 |  | 280 | 0 |  | 1
705 | 118 | Glass Block | Allowance |  |  |  | 0 |  |  | 0 |  | 1
825 | 119 | Final Cleaning |  | 850 |  |  | -850 |  | 850 | 0 |  | 1
807 | 120 | Special Equipment |  | 0 |  |  | 0 |  |  | 0 |  | 1
| 121 | Loan costs |  |  | 4424.86 |  |  | 0
| S.8 | Total Interior Finishing |  | 70381 | 28834.4643 | 0 | -41546.5357 | 10440.5847 | 37168.0547 | 28834.4643
|  | Project Cost Summary | [9 empty] | 109
| S.1 |  | Pre-Construction Costs (Permits/Fees) | 3292 | 12535.17 | 0 | 9243.17 | 304.75 | 0 | 12535.17
| S.2 |  | Site Construction Costs | 40342 | 35698.19 | 0 | -4643.81 | 25685.35 | 6261.63 | 35698.19
| S.3 |  | Site Preparation Costs | 31005 | 15578 | 0 | -15427 | 11478 | 16005 | 15578 | Total living: 2816
| S.4 |  | Foundation Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Garage: 804
| S.5 |  | Slab Work Costs | 45100 | 45600.64 | 0 | 500.64 | 44775.64 | 0 | 45600.64 | Porch: 338
| S.6 |  | Main Structure Costs | 42730 | 41415.69 | 0 | -1314.31 | 41415.69 | 0 | 41415.69 | Covered patio:
| S.7 |  | General Trades Costs | 127694 | 89856.26 | 0 | -37837.74 | 83323.03 | 45196.65 | 89856.26 | Total area: 3954
| S.8 |  | Interior Finishing | 70381 | 28834.4643 | 0 | -41546.5357 | 10440.5847 | 37168.0547 | 28834.4643 | $ per sq ft 124.55
|  |  | Job Total | 360544 | 269518.4143 | 0 | -91025.5857 | 217423.0447 | 104631.3347 | 269518.4143
210 |  |  | Overall Contingency Percentage |  | 74.75% |  |  | 67.51% | 32.49% | 0
208 |  |  | Sales Tax (if applicable) |  |  |  | 0 |  |  | $0.00
|  |  | Job Total | 360544 | 269518.4143 | 0 | -91025.5857 |  |  | 269518.4143
322054.3794
Note on D2: Shows a running display of the total so you don't have to go to the end of the spreadsheet everytime you want to know what the new total is.

## IndyMac Line Item Cost
LINE ITEM COST BREAKDOWN
Borrower:
|  |  |  | Tel # |  | Permit # |  |  | Loan #
Project Address:
[6 empty] | Architect: |  |  | Tel#
Contractor:
|  |  |  | Tel # |  | Engineer: |  |  | Tel#
[5 empty] | Original |  |  | Line Item Description |  | Original
|  |  | Line Item Description |  | Budget |  |  |  |  | Budget
[5 empty] | A |  |  |  |  | A
A. PRE CONSTRUCTION COSTS:
| 101 | Architect, Engineering & Soils Study Fees |  |  | 1355 | 601 | Waterproofing decks, shower pans, etc. |  |  | 0
| 102 | Design Review/Plan Check Fees |  |  | 0 | 602 | Gutters, downspouts, sheetmetal |  |  | 1000
| 103 | Permits - City/County |  |  | 0 | 603 | Roof covering |  |  | 17156
| 104 | Utility Connection Fees |  |  | 0 | 604 | Windows |  |  | 3778
| 105 | School/Park/Misc. Taxes |  |  | 0 | 605 | Exterior doors |  |  | 7576
| 106 | Project Bonds |  |  | 1937 | 606 | Skylights |  |  | 0
| TOTAL PRE-CONSTRUCTION COSTS |  |  |  | 3292 | 607 | Glazing |  |  | 0
| 'B. "SITE" CONSTRUCTION COSTS: |  |  |  |  | 608 | Exterior siding (See Project Profile) |  |  | 0
| 201 | Temporary Utilities & Facilities |  |  | 2500 | 609 | Exterior trim |  |  | 0
| 202 | Special Inspections/Testing-Geo-tech, Structural |  |  | 0 | 610 | Stucco |  |  | 13205
| 203 | Job Security |  |  | 0 | 611 | Masonry veneer |  |  | 5038
| 204 | Equipment Rental |  |  | 570 | 612 | Ornamental Iron |  |  | 2500
| 205 | Jobsite overhead |  |  | 0 | 613 | Garage Doors |  |  | 2050
| 206 | UBuildIt Fees: Project Management/Supervision |  |  | 19572 | 614 | Exterior painting |  |  | 0
| 207 | General Contractor's office overhead/profit. |  |  | 0 | SUB-TOTAL EXTERIOR WEATHER-TIGHT |  |  |  | 52303
| 208 | State Sales Tax (where applicable) |  |  | 0 | 701 | Insulation |  |  | 6835
| 210 | Builder Contingency |  |  | 0 | 702 | Drywall/Plaster |  |  | 10470
| SUB-TOTAL GENERAL REQUIREMENTS |  |  |  | 22642 | 703 | Interior stairways |  |  | 0
| 301 | Demolition |  |  | 0 | 704 | Cabinetry |  |  | 11884
| 302 | Clearing/Stakeout |  |  | 0 | 705 | Finish Materials/Millwork |  |  | 15930
| 303 | Rough grading/shoring/excavation/fill |  |  | 15000 | 706 | Interior Doors |  |  | 1413
| 304 | Site retaining walls/waterproofing/backfill |  |  | 0 | 707 | Finish Hardware |  |  | 1250
| 305 | Site drainage |  |  | 0 | 708 | Finish Carpentry Labor |  |  | 5431
| 306 | Private septic system |  |  | 9000 | SUB-TOTAL DRYWALL/FINISH CARPENTRY |  |  |  | 53213
| 307 | Domestic Water well |  |  | 0 | 801 | Countertops |  |  | 6727
| 308 | Pump house & Pressure water system |  |  | 0 | 802 | Tub/shower/enclosures |  |  | 3847
| 309 | Environmental |  |  | 2800 | 803 | Interior painting/Wall Coverings |  |  | 0
| 310 | Off-site improvements |  |  | 0 | 804 | Hard surface finish flooring |  |  | 13348
| SUB-TOTAL SITE PREPARATION |  |  |  | 26800 | 805 | Carpeting |  |  | 2961
| 401 | Embedded hardware |  |  | 45100 | 806 | Built-in Appliances |  |  | 7100
| 402 | Ground Plumbing |  |  | 0 | 807 | Special Equipment (see property profile) |  |  | 12500
| 403 | Ground Mechanical |  |  | 0 | 808 | Security system |  |  | 0
| 404 | Ground Electrical |  |  | 3000 | 809 | Intercom |  |  | 0
| 405 | Underground utilities |  |  | 400 | 810 | Built-in Vacuum Cleaner |  |  | 0
| 406 | Foundation & Building retaining walls poured |  |  | 0 | 811 | Finish Plumbing |  |  | 0
| 407 | Concrete slab poured-house, garage |  |  | 0 | 812 | Plumbing Fixtures |  |  | 8920
| SUB-TOTAL FOUNDATION COMPLETE |  |  |  | 48500 | 813 | Finish Electrical |  |  | 0
| 501 | Structural masonry |  |  | 0 | 814 | Lighting Fixtures |  |  | 3100
| 502 | Rough framing materials |  |  | 26320 | 815 | Finish Heating, Ventilating, Air Cond. |  |  | 0
| 503 | Structural steel |  |  | 0 | 816 | Solar Backup |  |  | 0
| 504 | Modular or Sectional Mfg. Home |  |  | 0 | 817 | Bath Accessories |  |  | 0
| 505 | Package/Kit Home |  |  | 0 | 818 | Tub and Shower Doors/Mirrors |  |  | 1180
| 506 | Mfg. Trusses/components |  |  | 0 | 819 | Finish Grading |  |  | 0
| 507 | Rough framing labor |  |  | 16410 | 820 | Pool/Spa |  |  | 0
| 508 | Lightweight concrete interior floors |  |  | 0 | 821 | Hardscape-Driveway, Walkways, Steps |  |  | 16005
| 509 | Plumbing top-out |  |  | 10800 | 822 | Landscaping |  |  | 3000
| 510 | Rough heating, ventilation, air conditioning |  |  | 8200 | 823 | Irrigation System |  |  | 0
| 511 | Rough electrical |  |  | 11026 | 824 | Fencing including Gates |  |  | 0
| 512 | Fire protection sprinklers |  |  | 0 | 825 | Touch-up/Final Cleaning |  |  | 850
| 513 | Fireplaces incl. Flues |  |  | 1500 | SUB-TOTAL BUILDING COMPLETION |  |  |  | 79538
| 514 | Security & Communications pre-wiring |  |  | 0 | TOTAL "SITE" COSTS |  |  |  | 357252
| SUB-TOTAL BUILDING ROUGH-IN COMPLETION |  |  |  | 74256 | TOTAL PROJECT COSTS |  |  |  | 360544
I hereby certify that the above referenced numbers are accurate and complete to the best of my knowledge.
X
|  | Borrower |  |  |  | Date
X
|  | UBuildIt Representative |  |  |  | Date